## Slide 1
ACTIVATION & LAUNCH PLAN
Driving partner buy-in and real utilisation of the hub
A mostly-digital engagement plan, anchored by one launch roundtable
Convened by deCOALonize · mazingirakenya.org

## Slide 2
THE OBJECTIVE
Beyond sign-ups — to active use
Buy-in
Partners understand the value and want in
Funders & policymakers see it as credible
Journalists treat it as a go-to source
Utilisation
Members sign in regularly
Orgs join the directory and upload resources
Petitions get started; calls get convened
Sign-ups are vanity. The plan is engineered for the second column.
MazingiraKenya · Activation & launch plan

## Slide 3
STRATEGY AT A GLANCE
90% digital, 10% in the room
Digital engagement (ongoing)
Invite & onboard partners with quick guided walkthroughs
A steady content cadence: pulse, scanned items, pledge updates
Social amplification across X, TikTok, Facebook & Instagram
Partner spotlights and petition drives
WhatsApp & email nudges to bring people back
One launch moment
A single breakfast roundtable (~30 people) to demo the hub, earn press, and convert partners, funders and policymakers in person.
Momentum then lives online.
MazingiraKenya · Activation & launch plan

## Slide 4
CONVENE · DECIDE · ACT
The Coalition Room — where meetings produce action
One tap to meet
Embedded video room — no account, no install, no app store
Schedule a call and members get an auto calendar invite
Join from any phone; runs on Jitsi in the browser
Minutes in minutes, not weeks
Capture decisions & action items live — even by voice dictation
Generate a formatted PDF and share it before anyone leaves the call
Optionally record the session where your server allows
3 weeks → 3 min
from meeting to shared minutes
The sector's quiet failure is minutes that arrive weeks late, with no clear action. The Coalition Room turns every call into a decision record and a next step — instantly — which is exactly why partners will convene here.
MazingiraKenya

## Slide 5
DIGITAL ENGAGEMENT
The engine of adoption
1
Onboarding
Personal invites + a 3-minute guided walkthrough per org
2
Content cadence
Weekly pulse, scanned items and pledge-index updates worth returning for
3
Social amplification
Clippable cards for X, TikTok, Facebook & Instagram
4
Partner spotlights
Feature a member org's work each week to model good use
5
Petition drives
Launch demands that give partners a reason to log in and act
6
Nudges
WhatsApp broadcast + email digest to re-activate quiet members
MazingiraKenya · Activation & launch plan

## Slide 6
MAKE IT STICKY
Design for repeat use
✓
Org champions
Name one person per partner org responsible for the hub
✓
Directory profiles
Every org completes and owns its listing
✓
Resource uploads
Ask each partner for one real resource in the first fortnight
✓
County documentation
Turn field activity into map entries and voices
MazingiraKenya · Activation & launch plan

## Slide 7
THE ROLLOUT
Four phases, twelve weeks
1
Awareness
Wk 1–2
Teasers on raia & socials; press pre-brief
2
Onboard
Wk 2–5
Invites, walkthroughs, directory + resources filled
3
Activate
Wk 4–8
Launch event, petition drives, first convenings
4
Sustain
Wk 8+
Content cadence, spotlights, quarterly gap review
MazingiraKenya · Activation & launch plan

## Slide 8
THE LAUNCH EVENT
A breakfast roundtable, ~30 seats
Who's in the room
~12 partner organisations (coalition + prospective)
~8 funders & policymakers
~7 journalists / editors
~3 coalition hosts / demo leads
Format · 3 hours
Breakfast → 15-min live demo → moderated roundtable on a live front (e.g. Siaya nuclear) → partner sign-ups & press Q&A.
Why in person, once
Press coverage that seeds the digital campaign
Face-to-face trust with funders & policymakers
A content bank — photos & clips — for weeks of posts
Live sign-ups: leave onboarded, not just interested
MazingiraKenya · Activation & launch plan

## Slide 9
EVENT BUDGET
~30 guests · Nairobi · half-day
Item | Basis | KES
Venue + breakfast package | 30–35 covers × ~5,500 (4-star, hall + catering + basic AV) | 190,000
AV top-up (mics, screen, laptop) | half-day | 20,000
Branding, print, name tags, folders, prospectus | design + production | 40,000
Photography + short recap video | half-day coverage for social | 35,000
Facilitation / MC | 1 moderator | 20,000
Journalist facilitation | press kits + modest transport | 30,000
Logistics & contingency (~10%) | transport, buffer | 40,000
Estimated total |  | 375,000
≈ KES 375,000
about USD 2,900
Lean 4-star ~KES 300k · premium 5-star + fuller media ~KES 480k
Per guest all-in: ~KES 12,500. Venue rates: half-day packages run KES 3,000–6,500pp in Nairobi; premium venues carry more weight with funders and press.
Indicative Nairobi rates, 2025 · confirm with 2–3 venue quotes

## Slide 10
MEASURING SUCCESS
What we watch after launch
30
guests, ≥70% partners onboarded on the day
25+
active member orgs within 6 weeks
40+
resources uploaded in the first month
3
petitions live in quarter one
8+
media pickups from the launch
Weekly
sign-ins tracked per org
MazingiraKenya · Activation & launch plan

## Slide 11
Next steps
Confirm date, venue and guest list (partners, funders/policymakers, journalists).
Lock the launch budget and request 2–3 venue quotes.
Prepare the demo, press kit and social content bank.
Assign an org champion for every partner before launch day.
Go live digitally in parallel — the event seeds the campaign, it doesn't carry it.
mazingirakenya.org